## Sheet1
Real-Time Deepfake Detection in Video Streams project
S. No | Topic | Sub Topics | Explanation | Additional Requirements | Status
1 | Research & Understanding | Study Deepfake Techniques | Study how GANs, Autoencoders, FaceSwap work and identify detection techniques like CNNs and XceptionNet. | Research papers on GANs and deepfake detection. | In Progress
|  | Select Dataset | Choose datasets like FaceForensics++, DFDC, Celeb-DF with both real and deepfake videos. | Access to large datasets for training. | Celeb-DF Done 10 GB
2 | Environment Setup & Preprocessing | Set Up Development Environment | Install Python, TensorFlow/PyTorch, OpenCV, FFmpeg, and CUDA (for GPU). | IDE (VS Code/PyCharm), GPU or cloud setup. | cloud setup : Google Colab
|  | Data Preprocessing | Extract frames from videos, resize to uniform size, normalize, and perform face detection for focused analysis. | OpenCV, FFmpeg, Dlib.
3 | Model Design & Training | Model Architecture | Use CNNs like XceptionNet/MobileNet for frame analysis. For temporal data, use 3D-CNN or CNN+LSTM. | TensorFlow/PyTorch, pre-built models.
|  | Train the Model | Train with a train/validation/test split, apply data augmentation, and monitor performance metrics. | GPU, training scripts, dataset.
|  | Optimization | Apply model quantization and pruning for performance optimization and lower latency. | TensorFlow Lite, pruning tools.
4 | Real-Time Video Stream Integration | Real-Time Video Capture | Capture frames from webcam/live streams using OpenCV/FFmpeg for real-time processing. | OpenCV, FFmpeg, Webcam/Live Stream.
|  | Inference in Real-Time | Process frames through the trained model for real-time deepfake classification (Real vs Deepfake). | Model inference pipeline.
|  | Display Results | Show live results as text or overlays on the video stream (Real or Deepfake detected). | UI/Overlay development.
5 | Performance Optimization & Evaluation | Optimize for Low Latency | Use multi-threading and GPU acceleration for faster frame processing. | Multi-threading, CUDA, TensorFlow Lite.
|  | Evaluate the Model | Evaluate on test data, track accuracy, precision, recall, and F1-score. Test with real-time video feeds. | Metrics calculation, real-time testing.
6 | Deployment & Integration | API Development | Develop a REST API using Flask/FastAPI to process video input and return predictions. | Flask/FastAPI, server setup.
|  | Integration with Streaming Platforms | Integrate the detection system with platforms like YouTube, Facebook to flag deepfakes in live streams. | Platform API integration, cloud hosting.
|  | Deployment | Deploy model to cloud (AWS/Azure) or edge devices (using TensorFlow Lite for mobile/IoT devices). | Cloud/Edge deployment tools, TensorFlow Lite.
7 | Documentation & Final Report | Documentation | Document all steps of the process, from data preprocessing to model evaluation and deployment. | Document writing tools, examples.
|  | Final Report & Presentation | Prepare the final report and presentation with project results, challenges, and future improvements. | PowerPoint/LaTeX for report
| Celeb-DF | Official Dataset Gdrive Link: | https://drive.usercontent.google.com/download?id=1iLx76wsbi9itnkxSqz9BVBl4ZvnbIazj&export=download | 9.3 GB
|  |  | https://drive.usercontent.google.com/download?id=10NGF38RgF8FZneKOuCOdRIsPzpC7_WDd&export=download | 2.0 GB

## Sheet2
Real-Time Deepfake Detection in Video Streams project
Topic | Sub Topics | Progress/Done
Research & Understanding | Study Deepfake Techniques | In Progress
| Select Dataset | Celeb-DF Done 10 GB
Environment Setup & Preprocessing | Set Up Development Environment | cloud setup : Google Colab
| Data Preprocessing | need to be done
Model Design & Training | Model Architecture | need to be done
| Train the Model | need to be done
| Optimization | need to be done
Real-Time Video Stream Integration | Real-Time Video Capture | need to be done
| Inference in Real-Time | need to be done
| Display Results | need to be done
Performance Optimization & Evaluation | Optimize for Low Latency | need to be done
| Evaluate the Model | need to be done
Deployment & Integration | API Development | need to be done
| Integration with Streaming Platforms | need to be done
| Deployment | need to be done
Documentation & Final Report | Documentation | need to be done
| Final Report & Presentation | need to be done